## energy
Outcome | Indicators | Units | Baseline | 2024/25 Target | Current progress | Percentage Progress based on 2024/25 Target | Percentage Progress based on 2026/27 Target | Status based on 2024/25 Target | Status based on NST2 Midterm target | Major drivers of performance | Challenges | Catch up Plans | 2024/25 Actual Target (according to allocated budget) | 2025/26 Actual Target (according to available budget) | 25/26 SSP Target | 2026/27 Target | 27/28 | 28/29 | Responsibility for reporting | Data Source (e.g. Report)
Increased spatial access to electricity countrywide | Percentage of cells with access to electricity (on-grid) | Percent | 91 | 92 | 99 | 107.6% | 103.1% | COMPLETED | COMPLETED | - Implementation of RUEAP EPCs. -All Districts except for CoK have ongoing access projects |  |  | 92% | 94% | 94% | 96 | 98% | 100% | MININFRA, Energy Sector | MININFRA Reports
Increased spatial access to electricity countrywide | Percentage of Households with access to electricity (on/off grid) | Percent | 78.9 | 83 | 82.9 | 99.88% | 90.11% | GOOD | GOOD | - Implementation of RUEAP EPCs - Huge contribution of private operators in supply of solar home systems |  |  | 83% | 87% | 87% | 92 | 96% | 100% | MININFRA, Energy Sector | MININFRA Reports
Increased spatial access to electricity countrywide | Percentage of productive use areas with access to electricity | Percent | 86 | 89 | 89.4 | 100.4% | 95.11% | COMPLETED | GOOD | - Implementation of RUEAP EPCs - Proper implementation of presidential pledges |  |  | 89% | 92% | 92% | 94 | 97% | 100% | MININFRA, Energy Sector | MININFRA Reports
Increased network of street lights on new and existing national and urban roads | Number of Km of street lights installed | Km | 2227.62 | 2286 | 2227.62 | 97.45% | 82.35% | GOOD | GOOD |  |  | All new roads under construction or rehabilitation are provided with streetlight facilities in their scopes | 2285.9 |  | 2555.24 | 2705.22 | 2870.2 | 3189.02 | MININFRA, Energy Sector | MININFRA Reports
Enhanced electricity generation capacity while increasing the share of renewable energy | Percentage share of renewable energy in power generation mix | Percent | 51 | 51 | 51 | 100% | 94.8% | COMPLETED | GOOD | Additional 60 MW from import energy source Local Projects including Nyabarongo II(43.5MW) and Rukarara VI (9.7 MW) are still ongoing | Delay in construction of new hydro power plants | -Speeding up the construction of Nyabarongo II HPP -Completion and commissioning of Kore MHPP | 51% | 51% | 51% | 53.8 | 57.8% | 60% | MININFRA, Energy Sector | MININFRA Reports
Improved Power Transmission and Distribution Network for reliability of power supply | Losses in the transmission and distribution networks | Parent | 17.99 | 16.6 | 17.99 | 108.4% | 118.4% | COMPLETED | COMPLETED | - Reinforcment of Distribution network projects - construction of new substations (Nyagatare and Gicumbi) -Installation of static voltave compensators at Shango and Rwabusoro substations |  | - Completion of Distribution Management System (DMS) Project - Customer maping and upgrade of ustomer Management System (CMS) | 17.6% | 15.9% | 15.9% | 15.2 | 14.7% | 14.7% | MININFRA, Energy Sector | MININFRA, RURA Reports
Improved Power Transmission and Distribution Network for reliability of power supply | SAIFI (avg no of interruptions) | ' | 21.71 | 21 | 11.29 | 53.76% | 57.6% | SATISFACTORY | SATISFACTORY | - Reinforcment of Distribution network projects - construction of new substations (Nyagatare and Gicumbi) -Installation of static voltave compensators at Shango and Rwabusoro substations |  | - Completion of Distribution Management System (DMS) Project - Customer maping and upgrade of ustomer Management System (CMS) | 14.9 | 0.203 | 20.3 | 19.6 | 18.9 | 18.3 | MININFRA, Energy Sector | MININFRA, RURA Reports
Improved Power Transmission and Distribution Network for reliability of power supply | SAIDI (avg hrs without power) | Hours | 14.43 | 14.23 | 7.59 | 53.34% | 56.64% | SATISFACTORY | SATISFACTORY | - Reinforcment of Distribution network projects - construction of new substations (Nyagatare and Gicumbi) -Installation of static voltave compensators at Shango and Rwabusoro substations |  | - Completion of Distribution Management System (DMS) Project - Customer maping and upgrade of ustomer Management System (CMS) | 17.6 | 0.141 | 14.1 | 13.4 | 12.7 | 12 | MININFRA, Energy Sector | MININFRA, RURA Reports
Increased adoption of clean and efficient biomass cooking technologies | Percentage of Households using efficient biomass cookstoves (Tiers 3&4) | Percent | 30.6 | 40 | 32.8742 | 82.19% | 59.77% | GOOD | SATISFACTORY | - Government subsidies - Outreach awareness campaigns | -Budget gap (program underfunded) - No data collection mechanisms for Clean Cooking Technologies outside of Government Program | Engage MINECOFIN and relevant institutions to raise the necessary financing | 36.88% | 38.94% | 51% | 55 | 59% | 61% | MININFRA, Energy Sector | MININFRA Reports NISR EICV
Increased adoption of clean and efficient biomass cooking technologies | Percentage of households using clean non-biomass technologies (Tier 5) | Percent | 4.6 | 14 | 4.6535 | 33.24% | 15.01% | LOW | LOW |  | -Affordability of appliances and fuels ie electricity and gas. -Alternative solutions easily accessible (charcoal) -Lack of institutionnal coordination | - Government sshould continue to subsdise the subsector -Intensify awareness campaigns -Improve institutionnal coordination | 5% |  | 24% | 31 | 36% | 39% | MININFRA, Energy Sector | MININFRA Reports NISR EICV
Increased adoption of clean and efficient biomass cooking technologies | Percentage of large scale-users using efficient and clean cooking technologies | Percent | TBD | 20 | 0 | 0% | 0% | LOW | LOW |  | Delayed procurement process (initial tender was cancelled and re-launched) | Required funds have been raised and tender published for all targeted schools | 9 schools | 35 schools | 40% | 60 | 80% | 100% | MININFRA, Energy Sector | NISR EICV MININFRA Reports