## transport
Outcome | Indicators | Units | Baseline | 2024/25 Target | 2024/25 Actual Target (according to allocated budget) | Current progress | Percentage Progress based on 2024/25 Target | Percentage Progress based on 2026/27 Target | Status based on 2024/25 Target | Status based on NST2 Midterm target | Major drivers of performance | Challenges | Catch up Plans | 2025/26 Actual Target (according to available budget) | Current progress (2024/25) Detailed | SSP Target 25/26 | 2026/27 Target | SSP Target 27/28 | SSP Target 28/29 | Responsibility for reporting | Data Source (e.g. Report)
Improved quality of the road Network | Length of unpaved National roads upgraded to paved (Cumulative) | KM | 1729 | 1739.3 | 1739 | 1739.3 | 100% | 11.53% | COMPLETED | LOW | 10km of Ngoma-Ramiro are expected to be completed by end June 2025. | The delay of the production of local materials (aggregates and stone base) for Ngoma-Ramiro road | the coontractor is looking for alternative source of stone base and aggregates | 1778.3 | The overall projects performance contrubuting to NST2 in current FY stands at 26% and 10km are expected to be completed by end June 2025. | 1778.3 | 1818.3 | 1904.3 | 1941.3 | RTDA | MININFRA Reports
Improved quality of the road Network | Length of national paved road Rehabilitated | KM | 598 | 598 | 598 | 604.1 | 101% | 93.33% | COMPLETED | GOOD | Expropriation funds secured for some sections | Still have a dificit for Expropriation funds | Fund mobilization is ongoing with MINECOFIN | 620.3 | 604.1 | 620.3 | 647.3 | 676.3 | 711.3 | RTDA | MININFRA Reports
Improved quality of the road Network | Length of feeder roads rehabilitated (cumulative) | KM | 4187.5 | 4193 | 4193 | 4193 | 100% | 2.538% | COMPLETED | LOW | 6km of Rutsiro lot1 are expected to be completed by end June 2025. | Expropriation funds still an issue affecting smooth progress of the project | Consultations with the Ministry of Finance to secure required funds for expropriation. | 4253.7 | The overall projects performance contrubuting to NST2 in current FY stands at 16% and 6km are expected to be completed by end June 2025. | 4253.7 | 4404.2 | 4597.2 | 4797.6 | RTDA | MININFRA Reports
Improved public transport services countrywide and reduced traffic congestion in urban areas | Inter-city scheduled bus services scaled up across the country | KM | 14442 | 14508 | 14508 | 14508 | 100% | 56.9% | COMPLETED | SATISFACTORY | New Bus routes has been introduced: Nyanza(K)-Ruhuha-Nyanza(S), Huye-Gasoro-Ruhuha and Huye-Gasoro-Ruhuha-Nyanza(K) | No challenge | N/A | 14540 | 14508 | 14,540 (Increase:32km) | 14558 | 14,610 (Increase:52.5km) | 14,622 (Increase: 12.5km) | RTDA | MININFRA Reports
Improved public transport services countrywide and reduced traffic congestion in urban areas | Dedicated Bus Lanes(DBL) introduced in CoK | KM | 0.6 | 22.6 | 22.6 | 0.6 | 2.655% | 1.59% | LOW | LOW |  | Currently, the contracts have been suspended –awaiting clearance on DBL. | Waiting for further guidance | 32.69 | Road signs for DBL on a length of 0.6Km are already marked from Kigali Round about to former Kigali Prison Center but the DBL is not operational | 32.69 | 37.73 | 42.78 | 47.82 | CoK | MININFRA Reports
Improved public transport services countrywide and reduced traffic congestion in urban areas | Smart traffic management system introduced by the CoK | Percent | 10 | 30 | 30 | 0 | 0% | 0% | LOW | LOW |  | Delay of design study | Close follow up by CoK | 70 | Design is approved and contract is under process | 70 | 100 |  |  | CoK | MININFRA Reports
Improved public transport services countrywide and reduced traffic congestion in urban areas | CoK’s critical roads intersection upgraded | ' | 5 | 5 | 5 | 0 | 0% | 0% | LOW | LOW | Funds already mobilized under: 1. Kigali Urban Improvement Project (Gishushu, Chez Lando,Sonatube janctions) 2. Prince House-Giporoso-Masaka project ( Giporoso Junction) | No challenge | Expedite Procurement process | 0 | Procurement process ongoing: Works: Tender documents under review and Publication expected in June 2025 Supervision: Evaluation of shortlisted firms ongoing | 0 | 1 | 1 | 2 | RTDA | MININFRA Reports
Improved Air Transport Infrastructure and Services | Number of passengers carried per year by the National Carrier | ' | 1021000 | 1219386 | 1139218 | 799466 | 65.56% | 47.5% | SATISFACTORY | LOW |  | * DRC Airspace closure which resulted to suspension of 3 destinations.*Capacity/Aircraft constraints.This year the carrier faced Technical challenges that kept a number of Aircrafts for quite a number of days out of service. | *Catch up plans have been engaging in Aircraft Leasing. The carrier have successfully engeged in Two Aircrafts leases and works are in progress for a potential 3rd to catch up with required Capacity. | 1381848 | 799466 | 1381848 | 1683035 | 1875534 | 2109505 | ATL | MININFRA Reports
Improved Air Transport Infrastructure and Services | Number of destinations of National Carrier | ' | 23 | 26 | 26 | 24 | 92.31% | 85.71% | GOOD | GOOD |  | * Suspension of 3 destinations following DRC Airspace closure. *Capacity/Aircraft constraints. This year the carrier faced Technical challenges that kept a number of Aircrafts for quite a number of days out of service. This heavily undermined any work towards opening new destinations. | * There are seem to be no catch up plans for 24/25 given the year ends in a few days. The Airline look forward to catch up in forth coming FYs. | 26 | 24 | 26 | 28 | 29 | 29 | RwandAir | MININFRA Reports
Improved Air Transport Infrastructure and Services | Centre of Excellence for Aviation Skills (CEAS)/Academy established | Percent | 10 | 20 | 20 | 18 | 80% | 8.889% | GOOD | LOW | N/A | * Delay in getting non objection from AfDB. * Delay in finalizing co-funding agreement between AfDB & OPEC. | * Better coordination with AfDB to fast-track documents review and issuance of non-objection. *Fast-tracking of co-funding agreement between AfDB & OPEC. | 60 | 18 | 60 | 100 | 100 | 100 | ATL Akagera Aviation | MININFRA Reports
Improved Air Transport Infrastructure and Services | Volume of cargo handled in all airports(WB and other carriers) | Tons | 8470 | 12652 | N/A | 14139 | 111.8% | 43.69% | COMPLETED | LOW | *Enhanced Sales strategies. *Enhanced end to end customer services |  |  | 31038 | 14139 | 31038 | 32365 | 32676 | 32987 | ATL | MININFRA Reports