## watsan
Outcome | Indicators | Units | Baseline | 2024/25 Target | 2024/25 Actual Target (according to allocated budget) | Current progress | Percentage Progress based on 2024/25 Target | Percentage Progress based on 2026/27 Target | Status based on 2024/25 Target | Status based on NST2 Midterm target | Major drivers of performance | Challenges | Catch up Plans | 2025/26 Actual Target (according to available budget) | Current progress (2024/25) detailed | Annual Targets (2025/2026) | 2026/27 Target | Annual Targets (2027/2028) | Annual Targets (2028/2029) | Responsibility for reporting | Data Source (e.g. Report)
Increased access to drinking water | Percentage of villages with access to improved drinking water | Percent | 80 | 82 | 82 | 82 | 100% | 91.11% | COMPLETED | GOOD | 231 villages have been served from completed projects : 1. Rubavu : 12 villages (Volcano Belt phase1 WSS) 2. Muhanga : 42 Villages (From WSS Extensions) 3. Huye : 25 Villages (WSS Extensions,Ongoing SPRP) 4. Rusizi : 50 Villages (WSS Extensions,On-going SPRP) 5. Nyagatare : 21 Villages (WSS Extensions) 6. Musanze : 5 Villages (Volcano Belt) 7. Kigali : 23 Villages (Kigali network WSS) 8. Ngororero :45 Villages (Ngororero WSS) 9. Ngoma (Sake): 08 villages (Sake WSS ) |  |  | 84% | 82% | 85% | 90 | 95% | 100% | MININFRA, MINALOC, WASAC, WASH PARTNERS | NISR, Sector reports
Increased access to drinking water | Daily water production capacity increased | m3/day | 329652 | 368736 | 368736 | 343,736 | 93.22% | 67.66% | GOOD | SATISFACTORY | New WTP constructed (Sake: 11,000 m3 and Ngororero: 3,084m3) | 2 projects (25,000m3/day) not completed due to delays experienced in procuring electromechanical equipment and materials such as pumps (muhazi with12,000m3/d and Kivu belt of 13,00m3/d ) | Speed up the cmpletion of on-going projects (Muhazi is at 82.78% and kivu belt at 83.72%) ongoing projects | 411736 | 343,736 (Muhazi is at 78% and kivu belt at 81%) ongoing projects | 472036 | 508036 | 544036 | 688686 | MININFRA, WASAC, WASH PARTNERS | Sector reports
Increased access to drinking water | Percentage of HHs with access to improved water source (SSP Indicator) | Percent | 82.3 | 85 | 85 | 89.7 | 105.5% | 99.67% | COMPLETED | GOOD | 1. piped on premises 21.2% 2. Public taps 33.4% 3. Protected springs 31.2 Boreholes 2.8% 4. Protected wells and rain water around 1% |  |  | 92% | 89.7% (EICV7 ) | 88% | 90 | 95% | 100% | MININFRA, MINALOC, WASAC, WASH PARTNERS | NISR, Sector reports
Increased access to drinking water | Percentage of HHs with access with improved water sources within 500 m in rural | Percent | 56.8 | 59 | 59 | 42.5 | 72.03% | 66.93% | SATISFACTORY | SATISFACTORY |  | Water infrastructures are still limited in rural areas | Increasing Water infrastructures targetting planned settlement , |  | 42.5% (EICV7 Report) | 61.2% | 63.5 | 65.7% | 68% | MININFRA, WASAC, WASH PARTNERS | NISR, Sector reports
Increased access to drinking water | Percentage of HHs with access with improved water sources within 200 m in urban | Percent | 72.4 | 74.9 | 74.9 | 59.8 | 79.84% | 74.84% | GOOD | SATISFACTORY |  | Water infrastructures are still limited in Urban areas compared to population growth | Increasing Water infrastructures targetting planned settlement |  | 59.8% (EICV7) | 77.4% | 79.9 | 82.4% | 85% | MININFRA, WASAC, WASH PARTNERS | NISR, Sector reports
Increased access to drinking water | Percentage of HHs with access with improved water sources within the dwelling yard. (SSP Indicator) | Percent | 18 | 21 | 21 | 21 | 100% | 65.62% | COMPLETED | SATISFACTORY | 1. Piped water Into dwellings 4% 2. Piped water Into compound , yard 12.1% 3.Piped to neighbor(immediate vicinity):5.1% |  |  | 25% | 21% (EICV7) | 27% | 32 | 40% | 50% | MININFRA, MINALOC, WASAC, WASH PARTNERS | NISR, Sector reports
Increased access to drinking water | Nonfunctional water supply systems rehabilitated | ' | 432 | 73 | 73 | 10 | 13.7% | 2.315% | LOW | LOW | 1. 10 Propoor project completed | there were some appeals during procurement process which Delayed the projects to start as planned | Close follow-up of on-going nonfunctional water supply systems under rehabilitation (1. 10 Pro-poor WSS are ongoing 2. SPRP : 55 NFWSS are ongoing at 58%) | 122 | 10 | 223 | 432 | - | - | MININFRA, WASAC, WASH PARTNERS | Sector reports
Increased access to drinking water | Non-revenue water reduced | Percent | 39.5 | 38 | 38 | 37 | 166.7% | 29.41% | COMPLETED | LOW | 1. Implementation of Kazein project and Scale project 2. Provide require staff, materials and transport in projects areas 3. Isolation and monitoring inflow volume | Interim progress may mislead | update the annual progress by June 2025 | 35% | 37% | 35% | 31 | 28% | 25% | MININFRA, WASAC, WASH PARTNERS | Sector reports
Increased access to drinking water | Number of km of water supply network constructed | ' | 33476 | 34655 | 34655 | 35538.1 | 174.9% | 64.72% | COMPLETED | SATISFACTORY | 1. Extension of 455 km on development project (Karongi WASH, Gisagara WASH, Sake and Ngororero) 2. Extension of 82.1 km from Branches | Baseline was revised as GIS report closing the year 2023-2024 (35,001km) |  | 36000 | 35538.1 | 35308 | 36662 | 37377 | 38113 | MININFRA, WASAC, WASH PARTNERS | Sector reports
Increased access to drinking water | Number of km of water supply network upgraded and rehabilitated | Km | 1785.8 | 406.3 | 406.3 | 31.8 | 7.827% | 2.568% | LOW | LOW | Realized from Rehabilitation of Mutete-Zoko WSS | Budget allocation is limited compared to planned network to be rehabiliitaed. | Prioritize the project into FY 2025-2026 | 100km | 31.8km | 825.4 | 1238.1 | 1568.7 | 1785.8 | MININFRA, WASAC, WASH PARTNERS | Sector reports
Increased access to sanitation services | Percentage of households with access to improved sanitation facilities | Percent | 92 | 94 | 94 | 94.3 | 100.3% | 97.22% | COMPLETED | GOOD | 1. Pit latrine with solid slab 91% (urban 87.4% and rural 92.5%) 2. Flush toilets 3.3% (urban 10.4% and rural 0.2%) | None |  | 95% | 94.3% (EICV7 ) | 95% | 97 | 98% | 100% | MININFRA, MINISANTE, MINALOC | NISR, Sector reports
Increased access to sanitation services | Percentage of population with basic sanitation services | Percent | 72.1 | 73 | 73 | 72 | 98.63% | 96% | GOOD | GOOD | 79.6% unshared toilets in rural 55% unshared toilets in urban | Limited commitment of community to address sanitation fissues | To enhance commuty-based awareness compaigns on sanitation services | 73% | 72% (EICV7 ) | 74% | 75 | 76% | 77% | MININFRA, MINISANTE, MINALOC | NISR, Sector reports
Increased access to sanitation services | Sewerage treatment capacity increased | m3/day | 8330 | 8430 | 8430 |  | 0% | 0% | LOW | LOW |  | Masaka quick fix was supposed to add capacity of 100 m3/day but is not yet completed due to delay of project equipments. | The project equipment to be delivered at the beginning of next fiscal year 2025-2026 as per shipping schedule proposed by KAMPS. | 8430 | 8330 (Masaka quick fix is ongoing at 80%) | 8492 | 8534 | 8723 | 21223 | MININFRA, MINALOC, WASAC, CoK | Sector reports
Increased access to sanitation services | Solid waste management facilities constructed | ' | 3 | 3 | 3 | 3 | 100% | 50% | COMPLETED | SATISFACTORY |  | No project was planned to be completed for this FY | There are 2 ongoing projects Musanze and Nduba modern landfills) | 4 | 3 (there are 2 ongoing projects Musanze and Nduba modern landfills) | 4 | 6 | 7 | 8 | MININFRA, MINALOC, WASAC, CoK | Sector reports
Increased access to sanitation services | Fecal sludge treatment plants constructed | ' | 3 | 4 | 4 | 3 | 75% | 42.86% | GOOD | LOW |  | Masaka quick fix was supposed to be added but is not yet completed due to delay of project equipments. | There are 2 ongoing projects Masaka at 80% and Musanze FSTP at 32% | 5 | 3 (there are 2 ongoing projects Masaka at 80% and musanze FSTP at 32%) | 6 | 7 | 7 | 8 | MININFRA, MINALOC, WASAC, CoK | Sector reports